## Overview
Phase | Goal | Primary Owner | Status | Notes
0. Handoff intake and architecture setup | Understand the prototype and create clean production foundations before moving UI. |  | Not Run
1. Source model and source button | Implement the selected source system used by dashboard, filters, add trade, and trades ledger. |  | Not Run
2. Source window | Build the source window as the main selector for sessions, journals, strategies, and comparison targets. |  | Not Run
3. Filter model and filter button | Implement filters that can be applied consistently to dashboard and trades page. |  | Not Run
4. Filter window content | Build the full filter window with source-aware options and no ambiguous filters. |  | Not Run
5. Central trade math and validation | Create a single calculation and validation layer used by add trade, edit trade, trades page, and dashboard. |  | Not Run
6. Add trade source selection and warning flow | Make Add Trade route the user through the correct source before editing. |  | Not Run
7. Add trade modal - Trade and Risk | Implement the main add/edit trade page with price, risk, timing, and summary behavior. |  | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | Implement context capture without confusing auto/manual semantics. |  | Not Run
9. Trades ledger page | Implement the filtered, source-aware trades page and row detail behavior. |  | Not Run
10. Trade detail box and edit flow | Make detail boxes and edit modal share identical calculations and labels. |  | Not Run
11. Final hardening and regression | Remove lag, layout drift, and hidden calculation mismatches before release. |  | Not Run

## Phase Checklist
Phase | Item Type | Checklist Item | Priority | Status | Owner | Notes
0. Handoff intake and architecture setup | Implementation | Treat TalariaV8b.jsx as a reference prototype, not production architecture. | Medium | Not Run
0. Handoff intake and architecture setup | Implementation | Create modules for source state, filters, trade math, validation, add/edit trade state, and shared UI components. | Medium | Not Run
0. Handoff intake and architecture setup | Implementation | Create one design token file for Talaria colors, typography, spacing, borders, motion, and z-index. | Medium | Not Run
0. Handoff intake and architecture setup | Implementation | Create shared UI primitives before feature windows: ModalShell, TopBarButton, Dropdown, Checkbox, Tooltip, DateTimePicker, NumericStepper, TagSelect, ScreenshotGrid, RiskRewardBar. | Medium | Not Run
0. Handoff intake and architecture setup | Implementation | Add a story, fixture page, or dev route that can render each shared component in every state. | Medium | Not Run
0. Handoff intake and architecture setup | Logic | No trade calculation should live only inside a React view. | High | Not Run
0. Handoff intake and architecture setup | Logic | No source or filter draft should affect dashboard/trades until the user confirms it. | High | Not Run
0. Handoff intake and architecture setup | Logic | All repeated UI states must use the same tokens and reusable components. | High | Not Run
0. Handoff intake and architecture setup | QA Gate | Build passes. | High | Not Run
0. Handoff intake and architecture setup | QA Gate | Shared components render in normal, hover, active, selected, disabled, error, and loading states. | High | Not Run
0. Handoff intake and architecture setup | QA Gate | The codebase has one source of truth for colors, spacing, motion, and trade math. | High | Not Run
1. Source model and source button | Implementation | Add source domain models for BacktestSession, LiveJournal, StrategySource, StrategyChildSource, Connection, Account. | Medium | Not Run
1. Source model and source button | Implementation | Support single-source and multiple-source modes. | Medium | Not Run
1. Source model and source button | Implementation | Support strategy selection with child source inclusion/exclusion. | Medium | Not Run
1. Source model and source button | Implementation | Support live journals grouped into personal accounts and prop accounts. | Medium | Not Run
1. Source model and source button | Implementation | Support connection grouping under personal/prop accounts. | Medium | Not Run
1. Source model and source button | Implementation | Create source button in the top bar with fixed dimensions and stable text truncation. | Medium | Not Run
1. Source model and source button | Implementation | Source button must show source type and source name. Multiple mode shows the number of selected sources. | Medium | Not Run
1. Source model and source button | Implementation | Do not put trades count inside the source button. Trades count belongs near the page title/evidence strip. | Medium | Not Run
1. Source model and source button | Logic | Draft source selection is separate from applied source selection. | High | Not Run
1. Source model and source button | Logic | Source changes affect dashboard/trades only after Go is clicked. | High | Not Run
1. Source model and source button | Logic | When switching from multiple mode to single mode, keep exactly one selected source. | High | Not Run
1. Source model and source button | Logic | When switching from single to multiple mode, preselect the currently selected source. | High | Not Run
1. Source model and source button | Logic | A strategy can be selected as one source, while its child sources can be included/excluded. | High | Not Run
1. Source model and source button | Logic | Child source selection is allowed only inside a strategy context. | High | Not Run
1. Source model and source button | Logic | Live accounts cannot show multiple markets in one account row. Use one market per account row. | High | Not Run
1. Source model and source button | Logic | Live account account type must be one of Live, Challenge, Funded, or Demo/Prop depending on account model. | High | Not Run
1. Source model and source button | QA Gate | Single-source selection updates source button after Go. | High | Not Run
1. Source model and source button | QA Gate | Multiple-source selection updates source button after Go. | High | Not Run
1. Source model and source button | QA Gate | Cancel restores previous applied source. | High | Not Run
1. Source model and source button | QA Gate | Strategy child source exclusions persist when reopening the source window. | High | Not Run
1. Source model and source button | QA Gate | Live journal personal/prop grouping counts are correct. | High | Not Run
1. Source model and source button | QA Gate | No row selection lag or delayed checkbox update. | High | Not Run
2. Source window | Implementation | Use a two-section window: source tree on the left, content list on the right. | Medium | Not Run
2. Source window | Implementation | Left tree includes Backtest Sessions, Live Journals, Strategies. | Medium | Not Run
2. Source window | Implementation | Live Journals contain Personal Accounts and Prop Accounts groups. | Medium | Not Run
2. Source window | Implementation | Right content uses consistent row cards for backtests, journals, and strategies. | Medium | Not Run
2. Source window | Implementation | Rows must show name, strategy/setup, market, progress if applicable, PnL %, trades count, and source status icon. | Medium | Not Run
2. Source window | Implementation | Strategy rows can expand; allow only one strategy expanded at a time. | Medium | Not Run
2. Source window | Implementation | Strategy child rows are informational unless child inclusion is enabled by the strategy selection behavior. | Medium | Not Run
2. Source window | Implementation | Bottom bar contains selected summary, Cancel, and Go. | Medium | Not Run
2. Source window | Logic | Backtest status icon summarizes rollback, real-world costs, and edited trade database status. | High | Not Run
2. Source window | Logic | Journal status icon summarizes edited vs unedited journal status. | High | Not Run
2. Source window | Logic | Strategy source status icon summarizes child source statuses in one info box. | High | Not Run
2. Source window | Logic | Source info boxes must aggregate mixed statuses instead of showing separate duplicated icons. | High | Not Run
2. Source window | Logic | Adding a trade to an unedited journal must warn that its status will become edited. | High | Not Run
2. Source window | Logic | Warning should support Cancel, Proceed, and Do not show again. | High | Not Run
2. Source window | QA Gate | Window does not close on outside click. | High | Not Run
2. Source window | QA Gate | Close button closes in one click, including compare/source mode. | High | Not Run
2. Source window | QA Gate | Hover and selection reactions are distinct and immediate. | High | Not Run
2. Source window | QA Gate | Info boxes appear after one second, within 4 px of cursor, with project-style vertical glow. | High | Not Run
2. Source window | QA Gate | Scrollbar appears only where content requires it. | High | Not Run
3. Filter model and filter button | Implementation | Create filter state model: date range, timing, trade scope, tags, strategy when applicable. | Medium | Not Run
3. Filter model and filter button | Implementation | Create filter button in the top bar with fixed size and stable text. | Medium | Not Run
3. Filter model and filter button | Implementation | Filter button shows No Filters or the number of active filters. | Medium | Not Run
3. Filter model and filter button | Implementation | Clear filters icon appears inside the filter button only when filters are active. | Medium | Not Run
3. Filter model and filter button | Implementation | Move filtered trade count to the evidence strip near page title, not inside the filter button. | Medium | Not Run
3. Filter model and filter button | Implementation | Opening another popover/window should close the current filter window in one click. | Medium | Not Run
3. Filter model and filter button | Logic | Filters apply to the active applied source set. | High | Not Run
3. Filter model and filter button | Logic | Filters affect both dashboard and trades page. | High | Not Run
3. Filter model and filter button | Logic | Filters must not change selected source state. | High | Not Run
3. Filter model and filter button | Logic | When a live journal is selected, include Strategy as a filter section. | High | Not Run
3. Filter model and filter button | Logic | When multiple live journals are selected, strategy filter options are the union of strategies used in included journals. | High | Not Run
3. Filter model and filter button | Logic | Tag filters must show source coverage so users understand how tag availability differs across selected sources. | High | Not Run
3. Filter model and filter button | QA Gate | No double-click required to switch from filter window to source window or add trade. | High | Not Run
3. Filter model and filter button | QA Gate | Clear filters works without opening the filter window. | High | Not Run
3. Filter model and filter button | QA Gate | Trades count near page title updates as filtered/total plus percentage. | High | Not Run
3. Filter model and filter button | QA Gate | No filter causes invisible or zero-result states without clear feedback. | High | Not Run
4. Filter window content | Implementation | Window uses same upper bar style as source window. | Medium | Not Run
4. Filter window content | Implementation | Left side shows sections: Date Range, Timing, Trade Scope, Tags, Strategy if applicable. | Medium | Not Run
4. Filter window content | Implementation | Right side renders the selected section content. | Medium | Not Run
4. Filter window content | Implementation | Date Range uses two calendars and a data coverage list below calendars. | Medium | Not Run
4. Filter window content | Implementation | Timing supports day-of-week, multiple time ranges, and duration range with units. | Medium | Not Run
4. Filter window content | Implementation | Trade Scope supports market, symbol, direction, and outcome. | Medium | Not Run
4. Filter window content | Implementation | Tags supports pre-trade and post-trade tag groups with source coverage counts. | Medium | Not Run
4. Filter window content | Logic | Date range must never allow dates outside available data. | High | Not Run
4. Filter window content | Logic | When multiple sources have gaps, calendars show the global range but data coverage list explains source ranges below. | High | Not Run
4. Filter window content | Logic | Gray dates outside data scope are unselectable and do not change cursor. | High | Not Run
4. Filter window content | Logic | Timing defaults to no filters. | High | Not Run
4. Filter window content | Logic | If a timing checkbox is enabled, at least one valid option/range is required. | High | Not Run
4. Filter window content | Logic | For tag filters, selecting all options in one section resets that section to no filter. | High | Not Run
4. Filter window content | Logic | Each tag category can allow only the strategy-defined values for the selected source(s). | High | Not Run
4. Filter window content | QA Gate | Date calendars are fixed size and no right-side window scrollbar appears. | High | Not Run
4. Filter window content | QA Gate | Date values can be typed only as realistic dates. | High | Not Run
4. Filter window content | QA Gate | Invalid date range shows inline error and blocks applying. | High | Not Run
4. Filter window content | QA Gate | Timing ranges cap at five time ranges. | High | Not Run
4. Filter window content | QA Gate | Trade duration defaults to 1 to 60 when enabled. | High | Not Run
4. Filter window content | QA Gate | Tag coverage displays selected trades/source coverage clearly. | High | Not Run
5. Central trade math and validation | Implementation | Create tradeMath module for weighted averages, PnL, R multiple, risk, open quantity, planned vs actual, MAE/MFE, duration, cost, close type. | Medium | Not Run
5. Central trade math and validation | Implementation | Create tradeValidation module for impossible, missing, or out-of-scope values. | Medium | Not Run
5. Central trade math and validation | Implementation | Create instrument metadata map for pip/tick size, tick value, unit label, decimals, market, and allowed symbol list. | Medium | Not Run
5. Central trade math and validation | Implementation | Use the same tradeMath output everywhere: add trade summary, detail box, edit window, trades row values. | Medium | Not Run
5. Central trade math and validation | Logic | Long trade: stop loss must be below weighted entry, target must be above weighted entry. | High | Not Run
5. Central trade math and validation | Logic | Short trade: stop loss must be above weighted entry, target must be below weighted entry. | High | Not Run
5. Central trade math and validation | Logic | Exited size cannot exceed entered size. | High | Not Run
5. Central trade math and validation | Logic | Trade can save as open without exit values. | High | Not Run
5. Central trade math and validation | Logic | When full size is exited, trade status becomes Closed automatically. | High | Not Run
5. Central trade math and validation | Logic | Outcome remains Pending/blank until exit is set. | High | Not Run
5. Central trade math and validation | Logic | Risk is automatically calculated. It is not user-entered percent risk. | High | Not Run
5. Central trade math and validation | Logic | R:R must identify whether it is planned or actual. | High | Not Run
5. Central trade math and validation | Logic | Costs for backtests are inherited from session settings and locked. | High | Not Run
5. Central trade math and validation | Logic | Costs for live journals are editable. | High | Not Run
5. Central trade math and validation | Logic | MAE and MFE values must be realistic for direction and price path. | High | Not Run
5. Central trade math and validation | QA Gate | Same sample trade has identical values in row, detail, edit window, add/edit summary, and dashboard. | High | Not Run
5. Central trade math and validation | QA Gate | Extreme large values do not hide labels or break graphs. | High | Not Run
5. Central trade math and validation | QA Gate | Invalid values block Save and show field-level error styling. | High | Not Run
5. Central trade math and validation | QA Gate | Open trades save successfully without exit values. | High | Not Run
5. Central trade math and validation | QA Gate | Partial exit keeps trade open and open quantity correct. | High | Not Run
6. Add trade source selection and warning flow | Implementation | Add Trade opens a Choose Source window when multiple applied sources exist. | Medium | Not Run
6. Add trade source selection and warning flow | Implementation | Choose Source lists only currently applied sources and selected strategy children. | Medium | Not Run
6. Add trade source selection and warning flow | Implementation | List supports scrolling if there are many sources. | Medium | Not Run
6. Add trade source selection and warning flow | Implementation | After source selection, open Add Trade modal. | Medium | Not Run
6. Add trade source selection and warning flow | Implementation | If selected live journal is unedited, show warning before opening editor. | Medium | Not Run
6. Add trade source selection and warning flow | Implementation | If user confirms, continue and update source edit status after save. | Medium | Not Run
6. Add trade source selection and warning flow | Logic | Backtest source uses backtest costs and restrictions. | High | Not Run
6. Add trade source selection and warning flow | Logic | Live journal source allows editable costs and strategy selection. | High | Not Run
6. Add trade source selection and warning flow | Logic | Prop backtest source label should show Backtest (Prop) in gold. | High | Not Run
6. Add trade source selection and warning flow | Logic | Discipline tab appears only for live journal and live prop sources. | High | Not Run
6. Add trade source selection and warning flow | QA Gate | No warning for already edited journal. | High | Not Run
6. Add trade source selection and warning flow | QA Gate | Warning appears for unedited live journal. | High | Not Run
6. Add trade source selection and warning flow | QA Gate | Do not show again applies only to that warning category. | High | Not Run
6. Add trade source selection and warning flow | QA Gate | Selected source type controls all add trade pages correctly. | High | Not Run
7. Add trade modal - Trade and Risk | Implementation | Use fixed-size modal. Popovers may overflow outside modal instead of creating modal scrollbars. | Medium | Not Run
7. Add trade modal - Trade and Risk | Implementation | Top bar shows trade id, source name/type, computed status, computed outcome, and close button. | Medium | Not Run
7. Add trade modal - Trade and Risk | Implementation | Tabs are a flow: Trade & Risk, Tags, Discipline when applicable, Notes & Screenshots. | Medium | Not Run
7. Add trade modal - Trade and Risk | Implementation | Market, Symbol, Direction, Entry Time, Exit Time fit in a compact top row. | Medium | Not Run
7. Add trade modal - Trade and Risk | Implementation | Direction uses Long and Short buttons, not dropdown. | Medium | Not Run
7. Add trade modal - Trade and Risk | Implementation | Entry Time and Exit Time use date-time picker with calendar and clock in one window. | Medium | Not Run
7. Add trade modal - Trade and Risk | Implementation | Exit Time has project checkbox. If unchecked, trade is open and outcome is pending. | Medium | Not Run
7. Add trade modal - Trade and Risk | Implementation | Price grid columns: Entries, Take Profit, Stop Loss, Exit. | Medium | Not Run
7. Add trade modal - Trade and Risk | Implementation | Entries/TP/Exit max five rows. Single row uses dot marker; multiple rows use row numbers. | Medium | Not Run
7. Add trade modal - Trade and Risk | Implementation | Stop loss supports one price and a size equal to total entry size. | Medium | Not Run
7. Add trade modal - Trade and Risk | Implementation | Costs sit below stop loss and match price field dimensions. | Medium | Not Run
7. Add trade modal - Trade and Risk | Implementation | Excursion section sits above the summary bar. | Medium | Not Run
7. Add trade modal - Trade and Risk | Implementation | Summary bar shows remaining open amount, cost, R/R graph, MAE/MFE, planned reward, actual, risk. | Medium | Not Run
7. Add trade modal - Trade and Risk | Logic | Numeric steppers use pip/tick increments based on symbol metadata. | High | Not Run
7. Add trade modal - Trade and Risk | Logic | Click and hold on arrows repeats changes. | High | Not Run
7. Add trade modal - Trade and Risk | Logic | Date/time typed input must restrict day, month, year, hour, minute to realistic values. | High | Not Run
7. Add trade modal - Trade and Risk | Logic | Exit time cannot be earlier than entry time. | High | Not Run
7. Add trade modal - Trade and Risk | Logic | Summary updates while typing but does not commit invalid values as valid. | High | Not Run
7. Add trade modal - Trade and Risk | Logic | Save button is disabled only for true blockers, not for open trades missing exit. | High | Not Run
7. Add trade modal - Trade and Risk | Logic | Actual indicator in R/R graph is always gold. | High | Not Run
7. Add trade modal - Trade and Risk | Logic | MAE/MFE line is gray and sits behind/above colored risk/reward/actual bars without label overlap. | High | Not Run
7. Add trade modal - Trade and Risk | QA Gate | Long invalid SL/TP errors block save. | High | Not Run
7. Add trade modal - Trade and Risk | QA Gate | Short invalid SL/TP errors block save. | High | Not Run
7. Add trade modal - Trade and Risk | QA Gate | Holding numeric arrows repeats smoothly. | High | Not Run
7. Add trade modal - Trade and Risk | QA Gate | Opening date-time picker does not add modal scrollbars. | High | Not Run
7. Add trade modal - Trade and Risk | QA Gate | Summary labels never overlap in extreme cases. | High | Not Run
7. Add trade modal - Trade and Risk | QA Gate | Costs are locked/unlocked according to source type. | High | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | Implementation | Tags are loaded from the strategy used by the selected source. | Medium | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | Implementation | Live journal add trade shows Strategy selector at top of Tags page. | Medium | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | Implementation | Each tag category is a dropdown with one selected value per tag. | Medium | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | Implementation | Pre-trade tags use gold accent. Post-trade tags use purple accent. | Medium | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | Implementation | No Auto labels for tags. They are manual selections provided by strategy definitions. | Medium | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | Implementation | Discipline tab includes demon catcher inputs for live journal/live prop only. | Medium | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | Implementation | Notes & Screenshots page uses compact note area and two screenshot grids. | Medium | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | Implementation | Screenshot rectangles have identical dimensions, centered layout, max six each. | Medium | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | Implementation | Do not show plus/add screenshot tile when max is reached. | Medium | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | Logic | Tags for live journals depend on the selected strategy. | High | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | Logic | Discipline inputs are available only for leaks or journal discipline tracking. | High | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | Logic | Post-trade screenshots are disabled until exit is enabled/closed if required by product rule. | High | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | Logic | Screenshots accept only supported image types and max count. | High | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | QA Gate | Tag dropdowns close on outside click. | High | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | QA Gate | One value per tag category is enforced. | High | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | QA Gate | Strategy dropdown includes already-used strategies at top for live journals. | High | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | QA Gate | Discipline tab hidden for backtest sessions. | High | Not Run
8. Add trade modal - Tags, Discipline, Notes and Screenshots | QA Gate | Screenshot grids never create nested scrollbars for six items. | High | Not Run
9. Trades ledger page | Implementation | Trades page title row matches dashboard title row. | Medium | Not Run
9. Trades ledger page | Implementation | Evidence strip on right shows n filtered/total percentage and average hold. | Medium | Not Run
9. Trades ledger page | Implementation | Dashboard pages dropdown is hidden on Trades page. | Medium | Not Run
9. Trades ledger page | Implementation | Tabs: Overview, Risk & R, Excursion, Journal. | Medium | Not Run
9. Trades ledger page | Implementation | Columns button appears only on Overview tab. | Medium | Not Run
9. Trades ledger page | Implementation | Column selector supports saveable templates with delete X on each template chip. | Medium | Not Run
9. Trades ledger page | Implementation | Limit selected columns so nothing is hidden. | Medium | Not Run
9. Trades ledger page | Implementation | Rows use a card/table hybrid with consistent column widths and centered headers. | Medium | Not Run
9. Trades ledger page | Implementation | Column headers use sessions-page sorting arrow style where sorting makes sense. | Medium | Not Run
9. Trades ledger page | Implementation | Header stays sticky while scrolling. | Medium | Not Run
9. Trades ledger page | Implementation | Double-clicking a row opens details. Trade ID arrow also toggles details. | Medium | Not Run
9. Trades ledger page | Logic | Rows reflect the currently applied source and filters. | High | Not Run
9. Trades ledger page | Logic | Live journal rows include Strategy column. | High | Not Run
9. Trades ledger page | Logic | Multiple-source or strategy child-source views include Source column with child/session name. | High | Not Run
9. Trades ledger page | Logic | Source origin label can be Auto, Manual, Edited, Original, etc. Do not show redundant A letter. | High | Not Run
9. Trades ledger page | Logic | Columns must not overflow off the far right edge. | High | Not Run
9. Trades ledger page | QA Gate | Filtered trades page count matches filter button evidence strip. | High | Not Run
9. Trades ledger page | QA Gate | Sticky column header has no visual gap while scrolling. | High | Not Run
9. Trades ledger page | QA Gate | Sorting works on sortable columns and is disabled where useless. | High | Not Run
9. Trades ledger page | QA Gate | Column template delete button has separate red hover/click behavior. | High | Not Run
9. Trades ledger page | QA Gate | No hidden columns at max allowed column count. | High | Not Run
10. Trade detail box and edit flow | Implementation | Detail box border surrounds both main row and expanded content. | Medium | Not Run
10. Trade detail box and edit flow | Implementation | Detail content uses compact sections: Prices, Risk/R, Excursion, Timing, Journal. | Medium | Not Run
10. Trade detail box and edit flow | Implementation | Top chips order: trade id, auto/manual, original/edited, close type, win/loss. | Medium | Not Run
10. Trade detail box and edit flow | Implementation | Prices show entries, TP, SL, and exit, including size multipliers when multiple entries/targets/exits exist. | Medium | Not Run
10. Trade detail box and edit flow | Implementation | Entry values blue, TP green, SL red, exit gold. | Medium | Not Run
10. Trade detail box and edit flow | Implementation | Show pre-trade and post-trade tags. | Medium | Not Run
10. Trade detail box and edit flow | Implementation | Show notes and demons if present. | Medium | Not Run
10. Trade detail box and edit flow | Implementation | Edit Trade opens the same Add Trade modal populated with exact row/detail values. | Medium | Not Run
10. Trade detail box and edit flow | Logic | Detail summary bar must use same tradeMath snapshot as edit window. | High | Not Run
10. Trade detail box and edit flow | Logic | MAE/MFE fields in edit must populate from existing trade detail data. | High | Not Run
10. Trade detail box and edit flow | Logic | Excursion fields and summary bar must stay in sync. | High | Not Run
10. Trade detail box and edit flow | Logic | If a user edits and saves, row, detail, dashboard, and filters update from the same saved trade object. | High | Not Run
10. Trade detail box and edit flow | QA Gate | Trade 1-t1 values match in row, detail, and edit window. | High | Not Run
10. Trade detail box and edit flow | QA Gate | MAE/MFE values match between detail summary and edit summary. | High | Not Run
10. Trade detail box and edit flow | QA Gate | Multiple entries/TP/exits display clearly in the detail box. | High | Not Run
10. Trade detail box and edit flow | QA Gate | Edit/save round trip does not alter unchanged values. | High | Not Run
11. Final hardening and regression | Implementation | Run a focused performance pass on click and hover handlers. | Medium | Not Run
11. Final hardening and regression | Implementation | Audit every dropdown for outside-click close and correct z-index. | Medium | Not Run
11. Final hardening and regression | Implementation | Audit all tooltips/info boxes for 1 second delay, within 4 px of cursor, and smooth pointer-follow. | Medium | Not Run
11. Final hardening and regression | Implementation | Run visual regression on source window, filter window, add trade pages, trades page, detail box, and edit modal. | Medium | Not Run
11. Final hardening and regression | Implementation | Create a seed dataset that includes open trades, closed trades, multiple entries, partial exits, live journals, prop accounts, strategies, edited journals, unedited journals, and extreme values. | Medium | Not Run
11. Final hardening and regression | Logic | No hidden state should use stale source/filter data. | High | Not Run
11. Final hardening and regression | Logic | No calculation can differ between row, detail, and edit. | High | Not Run
11. Final hardening and regression | Logic | No save path can bypass validation. | High | Not Run
11. Final hardening and regression | QA Gate | Production build passes. | High | Not Run
11. Final hardening and regression | QA Gate | No React hook order warnings. | High | Not Run
11. Final hardening and regression | QA Gate | No console runtime errors. | High | Not Run
11. Final hardening and regression | QA Gate | No visible lag between click and selected state. | High | Not Run
11. Final hardening and regression | QA Gate | QA workbook high-priority cases all pass. | High | Not Run

## QA Test Cases
Area | Scenario | Steps | Expected Result | Priority | Status | Tester | Notes
Source | Single backtest source | Select Standard Mode session, click Go. | Source button shows selected backtest and dashboard updates. | High | Not Run
Source | Multiple sources | Enable Multiple, select 3 sources, click Go. | Source button shows 3 sources selected; no stale counts. | Critical | Not Run
Source | Multiple off | With 3 sources selected, disable Multiple. | Only one source remains selected. | Critical | Not Run
Source | Strategy child persistence | Select strategy, exclude one child, Go, reopen. | Excluded child remains excluded. | High | Not Run
Source | Unedited journal warning | Add trade to unedited live journal. | Warning appears before editor opens. | High | Not Run
Filters | Date range full range | Open filter window with no filters. | Full range appears selected, no filter count. | Medium | Not Run
Filters | Out-of-range date | Type a date outside data coverage. | Inline error appears and Apply is blocked. | High | Not Run
Filters | Live journal strategy filter | Select live journal source and open filters. | Strategy section appears. | High | Not Run
Filters | Tag coverage | Select multiple sources with different tag sets. | Tag values show coverage counts and no ambiguity. | High | Not Run
Add Trade | Open trade save | Enter entry and stop, no exit, Save. | Trade saves as Open/Pending. | Critical | Not Run
Add Trade | Long invalid stop | Long entry 100, stop 110. | Field error appears; Save disabled. | Critical | Not Run
Add Trade | Short invalid target | Short entry 100, target 110. | Field error appears; Save disabled. | Critical | Not Run
Add Trade | Exit size too large | Entry size 1, exit size 2. | Field error appears; Save disabled. | Critical | Not Run
Add Trade | Full exit closes | Entry size 1, exit size 1 with exit time. | Status becomes Closed automatically. | Critical | Not Run
Add Trade | Backtest locked costs | Open backtest add trade. | Commission/spread prefilled and locked. | High | Not Run
Add Trade | Live editable costs | Open live journal add trade. | Commission/spread editable. | High | Not Run
Add Trade | MAE/MFE validation | Enter impossible excursion values. | Error style appears and Save blocks. | High | Not Run
Add Trade | Tags one value | Open one tag dropdown and select options. | Only one value per tag category can be selected. | Medium | Not Run
Trades | Filtered table count | Apply filter then open Trades page. | Title evidence row shows filtered/total count. | High | Not Run
Trades | Detail row open | Double-click a trade row. | Detail opens and row remains bordered with detail. | Medium | Not Run
Trades | Edit consistency | Open trade detail then Edit Trade. | Values match row/detail exactly. | Critical | Not Run
Trades | Column cap | Select maximum columns. | No hidden far-right column. | High | Not Run
Trades | Sticky header | Scroll far down. | Column titles remain visible without gap. | Medium | Not Run
Performance | Click response | Click source/filter/tabs rapidly. | State reaction appears immediately. | High | Not Run
Performance | Tooltip behavior | Hover status icon for one second. | Info box appears within 4 px of cursor and closes on mouseleave/scroll. | Medium | Not Run

## Logic Rules
Area | Rule | Priority | Implemented In | Validated By Test | Status | Notes
Source | Draft source changes must not affect dashboard or trades until Go is clicked. | Critical |  |  | Not Run
Source | Cancel must restore the previously applied source selection. | Critical |  |  | Not Run
Source | Switching multiple mode off must leave exactly one selected source. | High |  |  | Not Run
Source | Strategy child selections must persist after reopening the source window. | High |  |  | Not Run
Filter | Filter changes must affect dashboard and trades page consistently. | Critical |  |  | Not Run
Filter | Clear filters must be available without opening the filters window. | Medium |  |  | Not Run
Filter | Date range cannot include dates outside available data. | High |  |  | Not Run
Filter | Tag filter options must indicate coverage across selected sources. | High |  |  | Not Run
Add Trade | Open trades can be saved without exit values. | Critical |  |  | Not Run
Add Trade | Closed status is computed from exit timing/exit size, not chosen manually. | Critical |  |  | Not Run
Add Trade | Win/loss is computed only after exit data exists. | Critical |  |  | Not Run
Add Trade | Long trade requires stop below entry and target above entry. | Critical |  |  | Not Run
Add Trade | Short trade requires stop above entry and target below entry. | Critical |  |  | Not Run
Add Trade | Exit size cannot exceed entry size. | Critical |  |  | Not Run
Add Trade | Backtest costs are inherited and locked. | High |  |  | Not Run
Add Trade | Live journal costs are editable. | High |  |  | Not Run
Add Trade | Discipline tab appears only for live journal and live prop sources. | Medium |  |  | Not Run
Trades | Row, detail box, and edit modal must display the same calculated values. | Critical |  |  | Not Run
Trades | MAE/MFE in detail and edit must match stored excursion data. | High |  |  | Not Run
Trades | Column count must be capped so no columns disappear. | High |  |  | Not Run
UI | Hover/click/select states must be immediate and consistent. | High |  |  | Not Run
UI | Info boxes appear after one second and stay within 4 px of cursor. | Medium |  |  | Not Run

## Data Contract
Entity | Field | Implementation Note | Mapped Production Field | Status | Notes
Source | id | Stable unique id. Must not change between source window openings. |  | Not Run
Source | type | backtest, backtest_prop, live_journal, live_prop, strategy. |  | Not Run
Source | name | User-facing source name shown in source button and windows. |  | Not Run
Source | market | Single market for live account rows. Do not show mixed markets on one live account. |  | Not Run
Source | accountType | Live, Challenge, Funded, Demo, Prop when applicable. |  | Not Run
Source | connection | Broker/connection name such as MetaTrader 5, TradingView, cTrader. |  | Not Run
Source | status | Backtest or journal status summary used by source status icon. |  | Not Run
Source | children | Strategy child source ids for strategy source selections. |  | Not Run
Trade | id | Stable trade id shown in row and detail. |  | Not Run
Trade | sourceId | Source or child source owning the trade. |  | Not Run
Trade | strategyId | Required for live journal strategy filtering and tags. |  | Not Run
Trade | market/symbol | Market and symbol selected from allowed source instruments. |  | Not Run
Trade | direction | Long or Short. |  | Not Run
Trade | entryTime/exitTime | Exit time optional. Missing exit time means open trade. |  | Not Run
Trade | entries[] | One to five price/size rows. |  | Not Run
Trade | targets[] | Zero to five planned take profit rows. |  | Not Run
Trade | stop | One stop loss price with size equal to total entry size. |  | Not Run
Trade | exits[] | Zero to five actual exit price/size rows. Total size cannot exceed entry size. |  | Not Run
Trade | costs | Commission/spread/slippage. Locked for backtests, editable for live journals. |  | Not Run
Trade | excursion | Mode plus MAE/MFE values. Must be realistic and processable. |  | Not Run
Trade | tags | Pre and post tag selections from strategy definitions. |  | Not Run
Trade | discipline | Demon catcher fields for live journal/live prop only. |  | Not Run
Filter | dateRange | Start/end date inside selected source data coverage. |  | Not Run
Filter | timing | Days, time ranges, duration ranges. |  | Not Run
Filter | tradeScope | Market, symbol, direction, outcome. |  | Not Run
Filter | tags | Tag values with source coverage. |  | Not Run
Filter | strategy | Shown only when live journal source requires strategy filtering. |  | Not Run

## UI Standards
Component | Design Rule | Behavior Rule | Implemented In | Status | Notes
Modal/window shell | Top edge uses Talaria blue glow unless direction-specific add-trade rule applies. | No outside click close for Source/Add Trade. Filters may close on outside click. |  | Not Run
Top bar buttons | Fixed width, icon left of text, readable text, no layout shift. | Hover blue effect unless disabled. Disabled has no pointer cursor. |  | Not Run
Dropdowns | Darker list surface, clear border, top blue edge, vertical glow on selected/hovered option. | Close on outside click. No hidden bottom behind viewport. |  | Not Run
Checkboxes | Use project square checkbox style only. | Clicking label toggles checkbox where applicable. |  | Not Run
Tooltips/info boxes | Project style, vertical left glow, 1 second delay, within 4 px of cursor. | Disappear on scroll, mouseleave, or source movement away. |  | Not Run
Tabs | Horizontal glow under active tab, immediate hover/click reaction. | Flow arrows between Add Trade tabs use single bold arrow. |  | Not Run
Numeric inputs | Same field color and border across price, costs, date/time, excursion. | Steppers repeat on hold. Invalid values show red border and message. |  | Not Run
Date-time picker | Calendar and clock in one window, opens directly below button, no modal scrollbar. | Typing is restricted to realistic values. |  | Not Run
Risk/reward graph | Red risk area, green planned reward, gold actual, gray MAE/MFE line. | No overlapping labels. Animated quick changes. |  | Not Run
Trades table | Headers centered, sortable headers use sessions-page arrows. | Sticky header, equal readable spacing, no hidden columns. |  | Not Run

## Release Gate
Gate | Pass Criteria | Status | Owner | Notes
Build | Production build passes with no runtime errors. | Not Run
Console | No React hook warnings, undefined variables, or stale state errors. | Not Run
Source/Filters | Source and filter state are draft/applied correctly. | Not Run
Trade Math | Rows, details, edit, add trade, and dashboard match for seed trades. | Not Run
Validation | Impossible values are blocked and open trades are allowed. | Not Run
Performance | Click/hover/select reactions are immediate; no half-second lag. | Not Run
UX | Dropdowns, tooltips, checkboxes, tabs, modals match Talaria interaction rules. | Not Run
Regression | High and Critical QA cases pass. | Not Run