## Dashboard
TALARIA · DASHBOARD BUILD
Phase Verification — Progress Dashboard
Live roll-up of every phase. Update Status on the phase tabs; this page recalculates automatically.
Phase | Items | Pass | Fail | In Prog. | % Complete | Gates Passed
Cross-Phase Rules | 12 | 0 | 0 | 0 | 0% | 0 / 3
Phase 1 — MVP | 30 | 0 | 0 | 0 | 0% | 0 / 8
Phase 2 — Analytics | 23 | 0 | 0 | 0 | 0% | 0 / 8
Phase 3 — Finish | 32 | 0 | 0 | 0 | 0% | 0 / 20
TOTAL | 97 | 0 | 0 | 0 | 0%
OVERALL COMPLETE |  | 0%
⚠ A phase is only DONE when every GATE item on its tab shows Pass. Gates are hard blockers — do not start the next phase until all gates pass.
STATUS LEGEND
Pass | Fail | In Progress | Not Started | N/A

## Cross-Phase Rules
TALARIA · DASHBOARD BUILD
Cross-Phase Rules
Verify these in every phase — applies to Phase 1, 2 and 3
ID | GATE | Checklist item | Status | Verified by | Date | Notes
CROSS-PHASE RULES — verify in EVERY phase
X-01 | GATE | No Basic/Advanced toggle exists anywhere — single categorized navigation only. | Not Started
X-02 | GATE | Zero console errors on any navigation path. | Not Started
X-03 |  | Design tokens only — no hardcoded colors. Sharp corners (radius 0). No card drop-shadows. | Not Started
X-04 |  | Typography uses only the scale: 8 / 10 / 14 / 16 / 24 px. Section labels 8px weight 800 uppercase. | Not Started
X-05 |  | Tabular-nums on every number. Numbers right-aligned, labels start-aligned. | Not Started
X-06 |  | View-Mode (Dollars / % / R / Pips / Ticks / Privacy) correct on every monetary display in scope. | Not Started
X-07 |  | RTL: layout mirrors; charts and digits do NOT mirror. | Not Started
X-08 |  | Filter change re-renders visible components within 200ms at 5,000 trades (worker jobs show progress). | Not Started
X-09 |  | Missing-field stubs degrade gracefully ('data not available'), each flagged // TODO: engine must populate. | Not Started
X-10 |  | Hash routes bookmarkable; restore source + filter + component state. | Not Started
X-11 | GATE | Four modes behave per spec: Standard (opt-in prop toolkit), Prop (challenge configurator + variation optimizer + simulation), Live (private/prop + discipline + Demon Catcher), Strategy (merged + reconciliation). | Not Started
X-12 |  | Risk-adjusted metrics (Sharpe/Sortino/Calmar/CAGR/Kelly/SQN/Recovery/Ulcer) all sourced from metrics.ts; surfaced in Quant KPI Strip / Consistency / Rolling. | Not Started

## Phase 1 — MVP
TALARIA · DASHBOARD BUILD
Phase 1 — MVP
Shell · Primitives · Data layer + metrics.ts · ESSENTIALS (19) · EXCURSION (16)
ID | GATE | Checklist item | Status | Verified by | Date | Notes
SHELL & INFRASTRUCTURE
1-01 | GATE | Top bar present: logo, source selector, session selector, filter pills, View-Mode dropdown, breadcrumb. Compare + Export buttons present but disabled. | Not Started
1-02 | GATE | Side-nav shows ALL EIGHT categories; ESSENTIALS + EXCURSION active, other six greyed with 'coming soon'. | Not Started
1-03 |  | Source selector switches Standard / Live / Strategy fully; Prop Firm selectable and ESSENTIALS/EXCURSION still render for it. | Not Started
1-04 |  | Active item styling: 3px left accent, dim-blue bg, label in accent. Breadcrumb updates. | Not Started
1-05 |  | Last-viewed component persists to localStorage; defaults to Talaria Score on first open. | Not Started
1-06 |  | Navigation is a content swap (no reload); all state persists across navigation. | Not Started
PRIMITIVES (built + tested in isolation)
1-07 |  | GaugeRing, Sparkline, DotTrail, StackedRatioBar, ProgressBar, BoxPlotMini, HeatmapCell, KpiCard, ChartFrame, SubWindow. | Not Started
1-08 |  | SubWindow: draggable, resizable, header (title+pin+close), footer (Export PNG/CSV/JSON + Copy + Close), Escape + click-outside close, one at a time, 150ms fade+scale. | Not Started
DATA LAYER
1-09 | GATE | Trade + Session contracts implemented exactly as specified. | Not Started
1-10 | GATE | talariaScore() deterministic and matches formula (0.30 profit + 0.30 risk + 0.20 consistency + 0.20 discipline); cached on session. | Not Started
1-10b | GATE | metrics.ts risk-adjusted library built (Sharpe, Sortino, Calmar, CAGR, Kelly %, SQN, Recovery Factor, Ulcer Index); single source of truth, no ad-hoc recomputation. | Not Started
1-10c |  | Quant KPI Strip renders all 8 risk-adjusted metrics from metrics.ts with sparklines + healthy/marginal/poor bands. | Not Started
1-11 |  | subScores(), dayWinRate(), drawdownStats(), and standard aggregations built + memoized. | Not Started
ESSENTIALS (17) — each renders without error
1-12 |  | Talaria Score · Sub-Score Breakdown · Strategy Radar · KPI Strip · Quant KPI Strip · Equity Curve · Cumulative R Curve · Drawdown · Win/Loss Distribution. | Not Started
1-13 |  | Balance Waterfall · Performance Calendar · Daily P&L Heatmap · Performance by Instrument/Session/Day · Instrument Bubble · Streaks & Records · Consistency · Trade Journal · Best & Worst Trades · Performance Highlights. | Not Started
1-14 |  | Equity Curve tabs work (Equity / Cum P&L / Returns / Rolling 30 / vs Buy&Hold / vs Random); brush zoom; annotations. | Not Started
1-15 |  | Trade Journal rows show mini equity sparkline + rule-adherence dot; row hover highlights equity curve. | Not Started
EXCURSION (15) — each renders without error
1-16 |  | Session Stat Cards (7) · Excursion Stat Cards (7) · What-If Bars · Capture Ratio Histogram · Post-Exit MFE Curve · Post-Exit MFE by Setup. | Not Started
1-17 |  | MAE Distribution · MFE Distribution · During vs Total MFE Scatter · MAE vs MFE Scatter · Trade Path Cloud · Box Plots · Setup Comparison · Losers Recovery Rate · Per-Instrument Breakdown Table · Trade Duration Analysis. | Not Started
1-18 | GATE | Excursion components correctly read barCloseR[] / barHighR[] / barLowR[]. | Not Started
1-19 |  | Gross/Net toggle and Session-Warning include/exclude filters work. | Not Started
LEARNINGS FROM LAST YEAR'S BUILD (v1)
1-L1 |  | Persistent Current Balance pill in the top bar (respects Privacy mode); Live freshness indicator hook present. | Not Started
1-L2 |  | Equity Curve granularity selector (Daily/Weekly/Monthly/Quarterly/Yearly) + chart-type (Area/Line) + accumulation (Cumulative/Per-period) toggles. | Not Started
1-L3 |  | Daily P&L Heatmap has a weekly-total column on the right of the grid. | Not Started
1-L4 |  | Talaria Score shows a tier sublabel (Developing / Proficient / Strong / Elite); no separate star rating. | Not Started
1-L5 |  | Trade Journal rows show inline note icon + screenshot-count badge. | Not Started
1-L6 |  | Performance Highlights strip on the landing view (Best Setup / Instrument / Time / Day), detection shared with Edge Finder. | Not Started
1-L7 |  | Trade Duration Analysis built as three linked bucket charts (P&L / count / win rate) with median + average reference lines. | Not Started
PHASE 1 SIGN-OFF
1-20 | GATE | All 34 components render on sample data; all cross-phase rules pass. | Not Started
1-21 | GATE | Six non-Phase-1 categories remain greyed (no premature content). | Not Started

## Phase 2 — Analytics
TALARIA · DASHBOARD BUILD
Phase 2 — Analytical Depth
What-If Simulator · Statistical · Patterns & Behavior · Strategy Health (22 components)
ID | GATE | Checklist item | Status | Verified by | Date | Notes
REGRESSION GUARD
2-01 | GATE | Nothing from Phase 1 changed, restyled, or regressed. All 32 Phase-1 components still pass. | Not Started
WORKER INFRASTRUCTURE
2-02 | GATE | Web Worker harness built; jobs run off the main thread; UI stays responsive. | Not Started
2-03 |  | Jobs present: monteCarlo, coinFlip, tpslReplay, edgeFinder, behavioralScan, sequenceReorder, variableCombos. | Not Started
2-04 |  | In-flight jobs cancel on filter change; awaiting components show a 'computing…' state. | Not Started
NEW COMPUTED METRICS (memoized, tested)
2-05 |  | expectancyByTpSl, rollingMetric, autocorrelation, runsTest, correlationMatrix, tagCross, tagPerformance. | Not Started
2-06 |  | edgeFinderInsights, behavioralTags, tiltSeries, regimeStats, edgeDecay, optimalF, sequenceRisk. | Not Started
WHAT-IF SIMULATOR (5)
2-07 |  | Expectancy Heatmap · Simulated vs Actual Equity · TP/SL Optimizer · Planned vs Actual Discipline · Advanced Management Stats. | Not Started
2-08 | GATE | TP/SL Optimizer + Expectancy Heatmap replay barHighR[]/barLowR[] with SL checked BEFORE TP; flipped trades flash; live stats update. | Not Started
STATISTICAL (6)
2-09 |  | R-Multiple Distribution · Rolling Metrics · Monte Carlo & Pass Probability · Autocorrelation · Symbol Correlation Matrix · Win/Loss Runs Test. | Not Started
2-10 | GATE | Monte Carlo + Coin Flip complete under 5s; vs-Random shows confidence score + p-value. | Not Started
2-11 |  | Monte Carlo Prop-Firm tab shows clean 'Prop Firm source required' placeholder when source ≠ Prop Firm. | Not Started
PATTERNS & BEHAVIOR (8)
2-12 |  | Tag Cross-Analysis Matrix · Variables Analysis · Variables Ranking Table · Tag Performance Tables · Trade Flow (Sankey) · Edge Finder · Behavioral Tilt Timeline · Execution & Rule Adherence · Price Behavior Explorer · Market Regime Matrix. | Not Started
2-13 | GATE | Tag Cross-Analysis Matrix intersects pre × post tags, confidence-shades <5-trade cells, click-to-drill works. | Not Started
2-14 |  | Rule Adherence compares with-rules vs without-rules using rulesFollowed/rulesViolated. | Not Started
2-15 |  | Edge Finder surfaces plausible patterns; Behavioral flags ≥2 patterns on a trigger session. | Not Started
STRATEGY HEALTH (3)
2-16 |  | Edge Decay · Position Sizing (Optimal F) · Sequence Risk. | Not Started
2-17 |  | Sequence Risk reorder distribution runs in a worker; actual max-DD line shown. | Not Started
LEARNINGS FROM LAST YEAR'S BUILD (v1)
2-L1 | GATE | Variables Analysis: N-way tag-combination explorer (Single/Pairs/Triples), min-trades filter, top/bottom combos, win-rate-vs-P&L bubble scatter. Worker-backed. | Not Started
2-L2 |  | Variables Ranking Table: flat sortable per-variable stats (Trades/Win%/Avg R/P&L/PF/Max DD/Expectancy); negative-P&L flagged red. | Not Started
2-L3 |  | SQN (System Quality Number) computed and surfaced in Rolling Metrics + as a Quant KPI option. | Not Started
2-L4 |  | Trade Duration (Phase 1) upgraded to / confirmed as three-linked-bucket-chart layout. | Not Started
PHASE 2 SIGN-OFF
2-18 | GATE | Four categories un-greyed; all 24 Phase-2 components render on Standard/Live/Strategy. | Not Started
2-19 | GATE | PROP CHALLENGE, LIVE DISCIPLINE, STRATEGY SOURCE and EXPORT still greyed. | Not Started

## Phase 3 — Finish
TALARIA · DASHBOARD BUILD
Phase 3 — Prop Firm, Export & Finish
Prop Firm views · Export · Compare mode · Mentor links · Final polish
ID | GATE | Checklist item | Status | Verified by | Date | Notes
REGRESSION GUARD
3-01 | GATE | Nothing from Phases 1-2 changed or regressed. All Phase 1-2 components still pass. | Not Started
MODE / SOURCE WIRING
3-02 | GATE | Contracts populated: propChallenge (1-step/2-step, futures/forex, per-phase rules, drawdownType static/trailing/EOD), accountType, planAdherence/hypotheticalRr/demons, disciplineScore/demonLog, mergedSources. | Not Started
3-03 |  | New /utils built: dailyRuleUtilization, passProbability, ruleSensitivity, dailyLimitOptimize, variationOptimize, disciplineScore, planAdherenceEquity, reconcile, sourceAttribution. | Not Started
3-04 |  | Dormant overlays activated: Daily P&L Heatmap near-breach borders; Monte Carlo rule lines + Pass Probability gauge + preset comparison. | Not Started
PROP CHALLENGE CATEGORY (5) — prop-aware gating
3-05 | GATE | Gating correct: shown by default in Prop mode; opt-in in Standard/Strategy (after configuring a challenge); auto-on for Live prop accounts. | Not Started
3-05b | GATE | Challenge Configurator: asset class (futures/forex), structure (1-step/2-step/instant), firm presets, per-phase rules with drawdown type; writes propChallenge and gates the rest. | Not Started
3-06 |  | Rule Compliance & Utilization: phase-aware; correctly tracks static vs trailing vs EOD-trailing drawdown; near-miss days flagged. | Not Started
3-07 | GATE | Pass Probability & Simulation: gauge + failure-cause + preset comparison (FTMO/MyForexFunds/The5ers/FundedNext/Topstep/Apex) + combined 2-step probability; < 5s. | Not Started
3-07b | GATE | Variation Optimizer: sweeps STRATEGY variations AND CHALLENGE variations, ranks by pass probability, stars cells above threshold; worker-backed with grid caps. | Not Started
3-08 | GATE | Daily Limit Optimization: dual sliders, day-by-day re-simulation, Original vs Optimized (Improvement % / Days Saved / Risk Reduction %); lighter Standard variant works. | Not Started
3-08c |  | Whole category renders on a failing-evaluation session without error. | Not Started
LIVE DISCIPLINE CATEGORY (3) — Live only
3-LD1 | GATE | Category visible ONLY when source = Live. Untagged live trades enforced to be classified (According to plan / Out of plan / Missed trade). | Not Started
3-LD2 | GATE | Discipline Filter & Score: adherence donut + Discipline Score 0-100 (missed-trade weighted by hypotheticalRr) + score trend. | Not Started
3-LD3 |  | Plan-Adherence Equity: Actual vs Strategy curves with deviation-cost gap in $ and R; missed/out-of-plan cost cards. | Not Started
3-LD4 | GATE | Demon Catcher renders the ARENA UI (cards sized by frequency, boss-to-slay spotlight, fade/slain state, 8-in-a-row warning, Survival→Growth→Consistency→Profitability rail) — NOT a spreadsheet. | Not Started
STRATEGY SOURCE CATEGORY (2) — Strategy only
3-SS1 | GATE | Category visible ONLY when source = Strategy. Source Reconciliation: tag-mapping, instrument-mapping, date-range mode (union/intersection/custom), scale normalization (R/%/none), currency, conflict panel. | Not Started
3-SS2 | GATE | Cross-source views degrade gracefully (banners, hidden sub-visuals) until conflicts resolved — never show wrong numbers. | Not Started
3-SS3 |  | Source Attribution Breakdown: decompose aggregate by originSource + backtest-vs-live divergence + per-source KPI cards. | Not Started
EXPORT CATEGORY (2)
3-09 |  | Report Builder: templates, page + card selectors, cover options, format toggle (PDF/HTML/gallery), live preview, generate. Output respects View Mode + filters. | Not Started
3-10 |  | Comparison View: two sessions, overlaid equity curves, delta column, diff heatmaps, common-vs-unique trades, significance p-value. | Not Started
CROSS-CUTTING
3-11 |  | Compare mode: top-bar button enabled; inline comparison works from supporting components. | Not Started
3-12 |  | Mentor share links: encode source + session + component + filters + readonly; restore exact view (backend stubbed + flagged if needed). | Not Started
3-L1 |  | Live freshness indicator wired to actual Live sync state ('Updated Xs ago' / 'Live'). (v1 'auto-updating every 30s'.) | Not Started
FINAL POLISH
3-13 | GATE | Accessibility: nav landmark, aria-labels, keyboard nav (Tab/Enter/Arrows), visible focus, screen-reader announcement of active component. | Not Started
3-14 | GATE | RTL audit across all ten categories passes. | Not Started
3-15 | GATE | Performance: 200ms filter budget at 5,000 trades; all simulations in workers with progress + cancel; 60fps on scroll/filter. | Not Started
3-16 |  | View-Mode audit across every component. Empty/error states verified everywhere. | Not Started
WHOLE-DASHBOARD DEFINITION OF DONE
3-17 | GATE | All components across all ten categories render on sample sessions for every supported source. | Not Started
3-18 | GATE | Single categorized nav; PROP CHALLENGE prop-aware, LIVE DISCIPLINE Live-only, STRATEGY SOURCE Strategy-only; correct gating throughout. | Not Started
3-19 | GATE | Talaria Score deterministic · Tag Matrix intersects pre×post · TP/SL replay SL-before-TP · Monte Carlo + Pass Probability < 5s. | Not Started
3-20 | GATE | Sub-windows, Compare mode, Report Builder, mentor links all functional. | Not Started
3-21 | GATE | Zero console errors · no design-system violations · all performance + a11y + RTL budgets met. | Not Started

## How to Use
TALARIA · DASHBOARD BUILD
How to use this checklist
1. Work through the phase tabs in order: Phase 1 → Phase 2 → Phase 3.
2. For each row, set the Status dropdown (column E) to Not Started / In Progress / Pass / Fail / N/A.
The cell colors automatically: green Pass, red Fail, gold In Progress.
3. Fill in 'Verified by' and 'Date' when an item is checked, and use 'Notes' for anything that needs follow-up.
4. Rows marked GATE (red) are hard blockers. A phase is NOT done until every GATE row on its tab is Pass.
5. The Cross-Phase Rules tab applies to every phase — re-verify it at the end of Phase 1, 2 and 3.
6. The Dashboard tab rolls everything up automatically: pass/fail counts, % complete per phase, gates passed, and overall completion.
Recommended workflow:
• Hand Codex the matching phase prompt (TALARIA_PHASE_1_MVP.md, etc.) plus the reference PDF.
• As Codex reports each piece done, set its Status here and spot-check against the acceptance criteria.
• When the phase tab is 100% Pass and all gates are green, move to the next phase prompt.
Component tally: ESSENTIALS 19 · EXCURSION 16 · WHAT-IF 5 · STATISTICAL 6 · PATTERNS 10 · STRATEGY HEALTH 3 · PROP CHALLENGE 5 · LIVE DISCIPLINE 3 · STRATEGY SOURCE 2 · EXPORT 2.